## Summary
Dance Treasure Hunt PWA - MVP Estimates
Phase | Description | Hours | Week
1 | Project Setup & Infrastructure | 11 | 1
2 | Authentication & User Management | 14 | 1-2
3 | QR Code Scanning | 12 | 2
4 | Content & Progress System | 16 | 2-3
5 | Statistics & Reporting | 13 | 3
6 | UI/UX Polish & Testing | 21 | 3-4
TOTAL |  | 87
Timeline
Optimistic: | 3 weeks
Realistic: | 3.5 weeks
Conservative: | 4 weeks

## Detailed Tasks
Phase | Task # | Description | Hours
1 | 1.1 | Initialize React + Vite project with PWA support | 2
1 | 1.2 | Configure vite-plugin-pwa (manifest, service worker) | 3
1 | 1.3 | Set up Firebase project (Auth, Firestore, Storage) | 2
1 | 1.4 | Configure GA4 property and tracking | 2
1 | 1.5 | Set up project structure and routing | 2
2 | 2.1 | Registration form (name, email, password) | 3
2 | 2.2 | Consent checkbox with text | 1
2 | 2.3 | Firebase Authentication integration | 3
2 | 2.4 | User profile creation in Firestore | 2
2 | 2.5 | Login/logout flows | 2
2 | 2.6 | Session management and protected routes | 2
2 | 2.7 | Consent logging and storage | 1
3 | 3.1 | Camera permission handling | 2
3 | 3.2 | QR scanner component setup | 4
3 | 3.3 | QR code validation logic | 3
3 | 3.4 | Error handling (invalid QR, camera denied) | 2
3 | 3.5 | Scan success feedback UI | 1
4 | 4.1 | Video player component | 3
4 | 4.2 | Progress tracking in Firestore | 4
4 | 4.3 | Progress UI (completed/current/total) | 2
4 | 4.4 | Completion detection logic | 2
4 | 4.5 | Confetti celebration on completion | 3
4 | 4.6 | Completion state persistence | 2
5 | 5.1 | GA4 event tracking (scans, completions) | 3
5 | 5.2 | User statistics in Firestore | 3
5 | 5.3 | Basic user dashboard (personal stats) | 3
5 | 5.4 | Data export script (JSON/CSV) | 4
6 | 6.1 | Responsive mobile-first styling | 4
6 | 6.2 | Onboarding flow / how-it-works | 3
6 | 6.3 | Error states and messages | 3
6 | 6.4 | Loading states (spinners, skeletons) | 2
6 | 6.5 | PWA install prompt | 2
6 | 6.6 | Cross-browser testing | 4
6 | 6.7 | Basic offline support (progress caching) | 3

## Scope
IN MVP
✓ PWA (not native app)
✓ Simple registration (name + email + password)
✓ Consent checkbox
✓ Firebase Auth + Firestore
✓ QR Code scanning (camera)
✓ Video playback
✓ Progress tracking
✓ Confetti celebration
✓ GA4 event tracking
✓ Data export (manual)
✓ Basic offline support
OUT (Future Phase)
✗ Location verification (GPS)
✗ Social login
✗ Admin panel
✗ Multiple tracks
✗ Full offline video support
✗ Live event mode
✗ Push notifications

## Technical Notes
Technical Stack
Framework: | React + Vite
PWA: | vite-plugin-pwa
Backend: | Firebase (Auth, Firestore)
Analytics: | Google Analytics 4
QR Scanning: | html5-qrcode
iOS Support: | Safari - works with html5-qrcode
Android Support: | Chrome - full support
Geolocation: | Available if needed (dropped in MVP)